## Sheet1
Date | Entry | References Accessed
02.03.22 | Fixed issues I was having converting ros image topic to OpenCV image. Can now successfully view the live image from Turtlebot3 aswell as begin processing it. I also began watching through a number of video tutorial projects in OpenCV on youtube to learn how to implement the image processing techniques I will require for the project. | https://dabit-industries.github.io/turtlebot2-tutorials/14c-OpenCV2_CPP.html
http://wiki.ros.org/cv_bridge/Tutorials/UsingCvBridgeToConvertBetweenROSImagesAndOpenCVImages
https://www.youtube.com/watch?v=2FYm3GOonhk
03.03.22 | Started work on chosen line detection method, warping image (warp perspective) on left and right side of robot to get a better view of each of the lines on the road. | https://www.youtube.com/watch?v=2FYm3GOonhk
04.03.22 | Discovered fatal flaw with the method I was hoping to use for detecting and tracking the lines on the road. It completely fails when approaching any sort of corner (turns in the road/bus lane/parking spot). Abandoned this method and started researching other possible methods. Decided to begin work with a new method, implemented a colour mask and canny edge detector. Spent time tuning the variables on each of these so that the edge detector will only detect white lines. | https://www.youtube.com/watch?v=2FYm3GOonhk
https://docs.opencv.org/3.4/da/d5c/tutorial_canny_detector.html
https://www.youtube.com/watch?v=KEYzUP7-kkU
https://docs.opencv.org/3.4/d5/df9/samples_2cpp_2tutorial_code_2ImgTrans_2houghlines_8cpp-example.html
https://docs.opencv.org/3.4/d9/db0/tutorial_hough_lines.html
05.03.22 | Implemented HoughLinesP, and tuned its parameters using trackbars. This may require further tuning to ensure detected lines are correct. Attempted to apply GaussianBlur to original source image before Canny edge detection in an attempt to filter any noise out as well as try and reduce the amount of false/not-useful edge detections (i.e. roadsigns). The GaussianBlur requires more investigation, as it messed with the previously tuned output of the Canny edge detector and the HoughLinesP. | https://www.youtube.com/watch?v=KEYzUP7-kkU
https://www.youtube.com/watch?v=5yx5zpu6nk8&t=452s
https://docs.opencv.org/3.4/d5/df9/samples_2cpp_2tutorial_code_2ImgTrans_2houghlines_8cpp-example.html
https://docs.opencv.org/3.4/d9/db0/tutorial_hough_lines.html
https://www.opencv-srf.com/2018/03/gaussian-blur.html
05.03.22 | After some investigation I removed GaussianBlur as it was not improving the result of the edge detection but was instead impairing it. Decided to crop the top off of the image before doing any processing as being able to see the sky and upcoming roadsigns was causing unwanted edge and hough line detections. The processed image is now only the lower half of the original and provides a much more accurate tracking of the lines. The removal of the GaussianBlur also meant that I had to re-tune the HoughLineP values, moving the robot along the road and tuning it at specific spots (bus lane/stop, corner, straight) to be as good as possible. Finally I figured out a way too make use of the coordinates of the start and end of the Hough Lines, temporarily circling the start of the lines. From this I plan to use these pixel coordinates to calculate the distance between the left and right line, thus allowing me to find the centre of the lane and adjust the position of the robot accordingly. Essentially drawing an imaginary line through the middle of the lane for the robot to follow. | https://docs.opencv.org/3.4/d9/db0/tutorial_hough_lines.html
https://docs.opencv.org/3.4/da/d5c/tutorial_canny_detector.html
https://www.youtube.com/watch?v=2FYm3GOonhk
06.03.22 | Started work on the path planning part of the project. Currently investigating using the coordinates of the start and end of the generated HoughLinesP from each of the lines on the road to calculate the centre of the lane. I have implemented an algorithm to detirmine the best Hough lines to use, and then to calculate the centre of the lane from those lines. However early testing seems to suggest this will not be accurate enough on its own and will require further development as it struggles with sharp corners and the bus lanes included in the world model. This method seems promising and given time I believe I can make a reliable lane detector.
07.03.22 | Continued work with the HoughlinesP method, tweaking some of the values and also rewriting the algorithm to detirmine the best hough lines to use. It is now tracking 2 points, which I plan to use to create a more accurate path through the lane. There are some small issues with the current implementation and it will require some more tweaking for it to become reliable, but this method is promising.